## Sophie
Name: Sophie |  | Project Group 4:
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | Talking through project ideas, the teams availability and what we want out of the project | 0.5 | Everyone, Charli Absent | YES
1 | 2024-11-08 | Putting together an agenda for our group call tomorrow | 1 | Sophie | YES
1 | 2024-09-11 | Group Call to discuss putting together our project assignment | 0.5 | Everyone | YES
1 | 2024-10-11 | Watching some pygame tutorials and playing around with it | 2 | Sophie | YES
1 | 2024-11-11 | Adding ideas and input to the Canva board for the group call | 0.5 | Sophie | YES
2 | 13/11/2024 | Pygame videos | 2 | Sophie | YES
2 | 14/11/2024 | Adding an answers for our project assignment | 1 | Sophie | YES
2 | 2024-11-15 | Pygame Videos | 1.5 | Sophie | YES | Need to look more closely into sprints and projects based on space
2 | 2024-11-15 | Proofreading and Submission of Assignment Doc | 0.5 | Sophie | YES
2 | 2024-11-16 | Pygame Videos and Looking at space/astronaut sprites | 3 | Sophie | YES | Look into implemeting the sprites into a pygame
2 | 17/11/2024 | Trying to implement and draw my own Sprites, Pygame Videos | 4.5 | Sophie | YES
3 | 2024-11-18 | Call with Ellen and Molly - Jira and Putting together Agenda for tomorrow | 0.75 | Sophie, Ellen, Molly | YES | Make Agenda ✅
3 | 2024-11-19 | Call with everyone - molly assigning our tasks on Jira and making sure everyones happy | 0.5 | Everyone | YES
3 | 2024-11-22 | Reviewing some more pygame tutorials and loading own sprints Looking at how to implement the timer and lives in the game | 3 | Sophie | YES | workout how to implement and get the code to work for lives and a timer
3 | 2024-11-23 | Call with Molly, Ellen and Pheobe - starting to write the pygame code for the game | 2.25 | Sophie, Ellen, Molly, Pheobe | YES | lives and timer
3 | 2024-11-23 | Working on how to have lives ✅ - need to implement into our code and starting to implement asteroids | 2 | Sophie | YES | Get the asteroids to work and then can implement lives
4 | 2024-11-25 | Check in call for end of first sprint - what we are doing in this weeks sprint and making sure everyone is happy/on the same page | 0.5 | Everyone | YES | Starting next sprint and the game finalised this week
4 | 2024-11-26 | Call with some of the team and Luke for some questions. | 0.5 | Sophie, Ellen, Marisa | YES | Need to start implementing testing
4 | 2024-11-28 | Call with Arianne for queries | 0.25 | Sophie, Molly, Ellen, Phoebe, Faziah | YES
4 | 2024-11-29 | Implementing Collision and Lives for the game | 3 | Sophie | YES
4 | 2024-11-30 | Call with group, to catch up and see where we've got to - what's next for tasks still outstanding | 0.25 | Sophie, Ellen, Charli, Marisa, Faizah and Phoebe | YES
4 | 2024-11-30 | Looking at collision masks, and changing screen size and background to fit. Re-ordering the code after pulling from main to avoid conflicts | 2 | Sophie | YES
4 | 2024-11-01 | Added some new fonts to the game | 1 | Sophie | YES
5 | 2024-11-05 | Working on the readme file | 0.5 | Sophie | YES
5 | 2024-11-06 | Adding more information to the readme file and doing manual testing on our code | 3 | Sophie | YES
5 | 2024-11-07 | Adding the manual testing information with gherkin syntax to our documentation | 2.5 | Sophie | YES
5 | 2024-11-08 | Finishing the manual testing document and adding to the readme file | 2
Total time:

## Molly
Name: Molly |  | Project Group (Name/Number): 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | Talking through project ideas, the teams availability and what we want out of the project | 40 mins | Everyone | Yes
1 | 2024-11-07 | Added ideas to google sheet, built on some of the existing ideas | 30 mins | Me | Yes | Added ideas for projects based on the interests in the file
1 | 2024-11-09 | Discussed the project ideas and voted which idea to go witrh. We will be making an educational game with a space theme. We will all do some research and add to canva | 30 minutes | Everyone | Yes | - Need to add notes to canva and conduct research (all) - Attend next call on 12/11/24 to start compiling assignment document
2 | 2024-11-11 | Played around with Pygame, watced a few videos on youtube | 1hr 30 | Me
2 | 2024-11-12 | Played around with Pygame, watced a few videos on youtube | 2hr | Me | Yes | finished tutorialhttps://www.youtube.com/watch?v=jO6qQDNa2UY
2 | 2024-11-12 | Added my thoughts on the project scope / features of the game / project management style | 30 | Me
2 | 2024-11-12 | Group call to decide on what sort of game we want to do and what features we want. | 1 hr | Me, Ellen, Charlie, Faizah, Marisa, Phoebe | Yes | Need to add any notes to google doc
2 | 2024-11-13 | Sort out jira and project tracker spreadsheet | 30 min | Me
2 | 2024-11-14 | Call to chat about how we want to approach the project | 30 min | Me, phoebe, charli, ellen,faizah | Yes | Do some more pygame stuff over the weekend
3 | 2024-11-18 | Call with Ellen and Sophie, check jira board works and go through agenda for next week | 30 min | Me, Ellen, Sophie |  | Checked Jira was working and started adding tasks
3 | 2024-11-19 | Call with everyone -We decided how to split out the tasks and I assigned our tasks on Jira | 30 | Everyone | Yes
3 | 2024-11-19 | Set up the files and pushed to main branch so we can start coding | 10 min | Me | Yes
3 | 2024-11-20 | Meeting with Arianne to ask questions on how to approach the projects and testing | 20 mins | Me, Charli, Sophie, Marissa, Faizah?
3 | 2024-11-21 | Set up read me template and made some notes | 20 mins | Me | Yes
3 | 2024-11-22 | Did another pygame tutorial from my book | 2hrs
3 | 2024-11-23 | Call to start coding the main game function, set up the astronaut class, got the astronaut moving on the screen. Did mob programming as the first coding session so we could agree on the appraoch to use | 2hr25 | Me, Sophie, Ellen, Phoebe | Yes
3 | 2024-11-23 | got one asteroid to fall on the screen in a random area | 40min | Mi |  | Can't get multiple to fall - sorted
3 | 2024-11-24 | Started working on the start screen and came up with a name for the game, used ellens code but got asteroids to fall vertically | 2hr | Me |  | can't figure out how to get user to input their name - sorted
4 | 2024-11-25 | Call to see where everyone is ay. Started a new sprint and carried over any unfinished tasks | 30 min | Me, Ellen, Sophie, Phoebe, Faziah, Charli
4 | 2024-11-28 | Had call with Arianne to ask some more questions | 15min | Me, Ellen, Sophie, Phoebe, Faziah
4 | 2024-11-28 | trimmed the asteroid file, got it to print hot when the asteroid is hit | 15 min | Me
4 | 2024-11-27 | Moved the welcome screen into its own function | 30 mins | Me
4 | 2024-11-28 | Figuerd out how to take the users name, might be able to use this in the leaderboard if we have time to implement it | 40 min | Me
4 | 2024-11-29 | Fixed welcome screen so text input has a transparent background, refactored screenheight/screenwidth, tidied the collision function | 1hr | Me
5 | 2024-12-01 | added the game over function and implemented it when lives =0 | 1hr | Me |  | Couldn't get scrolling background to work, ellen fixed it
5 | 2024-12-02 | Catch up call, I was away at the weekend so Ellen and Phoebe caught me up. Charli showed us some sound effects she found, Ellen created a poll to see who wants to do what for the remaining tasks | 30 min | Me, Ellen, Phoebe, Charli
5 | 2024-12-04 | Did some work on the read me and updated requirements | 60
5 | 2024-12-05 | trimmed astronaut, removed files were not using, fixed where lives sits, limited characters in name,added some exception handling | 50 min | Me
5 | 2024-12-07 | Pair programming to refactor code, moved some functions around to make things cleaner | 2hr30 | Me, Ellen
5 | 2024-12-07 | More refactoring, fixing welcomescreen and gameover class | 2hr | Me
5 | 2024-12-08 | Fixed where facts are shown on screen, moves files into folders, fixed the issues that caused lol , proof reading docs | 3hr 30 | Me
Total time: 29 ish

## Ellen
Name: Ellen Parsonage |  | Project Group (Name/Number): 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | - Set up the activity log google sheet, and a google sheet for any ideas we have of what to base the project on - Agreed to add ideas for the project/our interests in the next few days - Aiming to finalise project idea by 9/11/24 so that we have some time to start putting together the project document for the assignment; call organised for 10:15am - Molly set up a GitHub repo for the project and added everyone as collaborators | 0:40 | All, Absent: Charli | Yes | - Input ideas for project on the googlesheet (all) - Attend call on 9/11/24 to finalise project idea and start planning assignment (all)
1 | 2024-11-07 | - Added ideas to the potential project ideas google sheet ahead of discussion at the weekend | 1:00 | Ellen | Yes | - API based app ideas: map of the world containing info about countries, focused on tourism or general knowledge; recipe randomiser for meals throughout a week; pet adoption; job application tracker - Game based ideas: looking after virtual pet, using data stored in DB, user can interact with the pet; space-centred snake style game where asteroids are dodged/stars collected
1 | 2024-11-09 | - Group call to discuss our project ideas; decided to focus on the game-based ideas, then made a poll of the 5 most popular concepts - An educational space-centred game was the top choice - Each team member to now research potential frameworks to use and add notes to the Canva whiteboard - Next group call planned for Tuesday evening post-session to discuss notes and organise compiling project plan document - Marisa recorded notes for the call and shared in the slack | 0:30 | All | Yes | - Need to add notes to canva and conduct research (all) - Attend next call on 12/11/24 to start compiling assignment document
2 | 2024-11-11 | - Conducted research and put together notes for Project Assignment (i.e., reason for creating the game, potential game types that could be simple to make using Pygame, use of a DB) and added to the group Canva | 2:00 | Ellen | Yes | - Present ideas to the rest of the group in call on 12/11/24
2 | 2024-11-12 | - Research potential groupwork methodology e.g., agile/Scrum, and tools such as Jira | 1:00 | Ellen | Yes | - Present ideas to the rest of the group in call on 12/11/24
2 | 2024-11-12 | - Group call to finalise our game design and discuss notes for the Project Assignment | 1:00 | All, Absent: Sophie | Yes | - Need to add our notes to Google sheet which will be proofread by Faizah and Phoebe - Need to add our finalised ideas in game thread set up by Charli - Need to research Jitsi (me)
2 | 2024-11-14 | - Transferred over my notes from the Canva whiteboard to the Project Assignment document, and tweaked the game design breakdown to ensure it was as clear as possible, and aligned with the decisions made in the Slack channel over the past few days | 0:30 | Ellen | Yes
2 | 2024-11-14 | - Group call to discuss how we're feeling about the project so far; unit testing; and how we plan to delegate coding tasks - Arianne joined the call to answer any queries we had; on the subject of work distribution, she suggested we assign roles based on our strengths, and ensure more than one person is not working on the same branch at the same time (which may affect how we split coding tasks) | 0:40 | All, Absent: Sophie, Marisa | Yes | - Conduct independent research over the weekend, including watching/reading the shared game tutorials (all) - Look into project presentation templates (me)
3 | 16/11/2024 - 18/11/2024 | - Followed tutorials for creating simple games in PyGame (saved resources to be shared with the group) - Added some tasks to backlog on Jira that aligned with the order of completion of game within tutorials - Created thread of questions to ask Arianne on Slack - Added links to presentation templates on Canva board, as well as some more thoughts about potential role breakdown | 5:00 | Ellen | Yes | - Discuss backlog tasks with group in call on 18/11/24 to begin delegating tasks/figure out what can be done concurrently (all) - Linked to the above, make note of team strengths and weaknesses, and desired roles
3 | 2024-11-18 | - Had a call with Sophie and Molly to discuss agenda for whole group call on 19/11/24; Sophie put together agenda - Molly added group to Jira in preparation to delegate backlog tasks in next call | 0:30 | Ellen, Molly, Sophie | Yes | - Tweak backlog tasks to fit with tutorial setup shared by Molly
3 | 2024-11-19 | - Group call to check everyone is happy with initial Jira stories/epics/tasks, and assign backlog tasks - Half the group (Charli, Marisa, Faizah) to focus on sourcing facts for game, setting up SQL database, and linking to python with the SQL connector - Other half (Molly, Sophie, Phoebe, Ellen) to focus on starting to compile code for the game, e.g., uploading sprite images, starting to put together classes for astronaut, asteroids and game loop - Forms our first Sprint, to be completed by 25/11/24 | 0:30 | All | Yes | - Call with Molly, Sophie and Phoebe on Saturday to compile code - Next group call 25/11/24
3 | 2024-11-23 | - Wrote out in pseudocode a draft of the initial class setup for the game - Updated Jira with tasks "In Progress" - Had coding session with Phoebe, Sophie and Molly; set up main.py file that contains game class and run function, set up astronaut.py file that contains astronaut class and update function to move the astronaut in game window (initialised in game class) | 2:00 | Ellen, Molly, Sophie, Phoebe | Yes | - Call with Molly on 23/11/24 to initiate the asteroid class and and draw them to screen
3 | 2024-11-24 | - Fixed bug in Sophie/Molly's code so that multiple asteroids fell throughout the game, amended Astronaut and Asteroid classes to make main.py code slightly cleaner | 1:00 | Ellen | Yes | - Continue with sprint tasks on 24/11/24, including implementing timer and/or changing the game background
4 | 2024-11-25 | - Added timer.py file including Timer class that prints time duration to the screen | 2:00 | Ellen | Yes
4 | 2024-11-25 | - Sprint Review on group call; discussed tasks still pending (asteroud/astronaut collision function, db/sql function), to be carried into next Sprint - New tasks input into Jira for next Sprint; to be delegated - Group call on 30/11/2024 mid-sprint to assess what we have left to do, start organising writing up report, tests, proofreading code | 0:35 | All, Absent: Marisa | Yes | - Complete code for scrolling background - Add tasks to Jira for new sprint
4 | 2024-11-25 | - Added scrolling_background function to main.py file, uploaded stars.jpg as the background | 1:30 | Ellen | Yes | - Push to main branch on GitHub
4 | 2024-11-26 | - Group call with Luke to ask queries about testing, exception handling, game complexity, specialisation content and use of classes - Also discussed potential use of itertools alongside database code | 0:35 | Ellen, Sophie, Marisa | Yes | - Evaluate class use
4 | 2024-11-27 | - Added more functions to Timer class to show the longest time/high score on screen, stored in file called high_score.txt | 3:00 | Ellen | Yes
4 | 2024-11-28 | - Group call with Arianne to ask queries about specialisation content required in project code, report and presentation content, game glitches such as sprite blurring when moving | 0:20 | All, Absent: Charli, Marisa | Yes
4 | 2024-11-30 | - Group call to ensure everyone's branches were up to date on GitHub, delegate last tasks for Sprint 2, and discuss potential tasks for Sprint 3; Jira updated | 1:00 | All, Absent: Molly | Yes | - Continue with high score/leaderboard code after pulling lives and health bar code from main - Look at potential unit tests
4 | 2024-12-01 | - Pushed code from feature1-ellen branch to main to include scrolling background on welcome screen, and high score timer - Started writing unit tests for timer.py file, researched mocking for sprite movement | 5:00 | Ellen | Yes | - Write unit tests for rest of timer file and look at unit tests for health bar - Look at mocking for key presses/events
4 - 5 | 1/12/2024 - 2/12/2024 | - Finished unit tests for timer.py file (utilising a timer_utils.py file for importing logic functions) - Repeated this for health_bar.py after moving it to its own class | 4:00 | Ellen | Yes | - Look at mocking
5 | 2024-12-02 | - Sprint review discussing what is left for final Sprint; Ellen to put a poll in the group for everyone to choose out of tasks remaining - Need to decide on fact display mode then all code from feature1-ellen pushed (including Molly's code for game over screen) | 0:20 | All, Absent: Sophie, Marisa, Faizah | Yes | - Put poll in slack for remaining backlog tasks
5 | 4/12/2024 - 5/12/2024 | - Created child class of SpaceGame class that inherited all features, but overwrote the run() function to simply open a pygame window, simulated key press event, check events, and return the astronaut's new position. Waiting on response from Arianne as to how best to format this test for all arrow keys - Delegated tasks on Jira for final sprint according to responses in the Slack poll | 5:00 | Ellen | Yes | - Update unit test files and push once Arianne has confirmed
5 | 2/12/2024 - 7/12/2024 | - Code Review - Made some notes on how we can improve our code structure in line with SOLID principles - Had a pair programming call with Molly to restructure our classes, particularly in main.py to ensure there were less dependencies on the SpaceGame class - Introduced ABC for the Welcome and Game Over screens, and carried out integration testing - Updated unit testing for astronaut movement - Proofread and edited Project Report, added diagrams, cut down to fit 7-page limit | 12:00 | Ellen, Molly | Yes | - Need to finalise Project Report and do another code read-through ahead of submission
5 | 2024-12-08 | - Finalised Project Report, bug-fixed testing files once sub-directories had been created - Final code review | 5:00 | Ellen | Yes
Total time:
51:40

## Charli
Name: | Charli | Project Group (Name/Number): Project Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-08 | Added ideas to Project Ideas sheet and read through other proposals. | 30 min | Charli | Yes
1 | 2024-11-09 | Group call discussing project, availabilities, choosing project concept etc. | 1hr | All | Yes
2 | 2024-11-11 | Created thoughts thread on Slack to help with meeting agendas and getting a foundation set in stone. Added own thoughts to thread. | 15 min | Charli | Yes
2 | 2024-11-11 | Researched sprite websites, made a bookmark on slack channel with the links | 10 min | Charli | Yes
2 | 2024-11-12 | Call to finalise game and written concept for Friday | 1hr | All except Sophie | Yes
2 | 2024-11-13 | Wrote out the answer for Q1 on the Project Assignment | 30 min | Charli | Yes
2 | 2024-11-16 | Researched the general build of a game in python as assigned to all group members | 2-3 hrs | Charli | Yes
3 | 2024-11-19 | Group call discussing agenda and assigned tasks | 30 min | All | Yes
3 | 2024-11-19 | Created Facts document and searched for 10 facts | 45 min | Charli | Yes
3 | 2024-11-23 | Researched and added 5 more facts to document | 1 hr | Charli | Yes
3 | 2024-11-23 | Created SQL DB for game | 2 hrs | Charli | Yes
4 | 2024-11-25 | Group call to discuss Jira sprints and address other items on agenda | 45 mins | All except Marisa | Yes
4 | 2024-11-25 | Uploaded meeting recording to Google drive | 5 min | Charli | Yes
4 | 2024-11-26 | Amended SQL code and pushed branch to github | 30 min | Charli | Yes
4 | 2024-11-26 | Researched sound effects, found a decent site to source all from and shared in group chat | 30 min | Charli | Yes
4 | 2024-11-27 | Updated .gitignore with config.py, created new config.py file with root info | 45 min | Charli
4 | 2024-11-27 | Call with Marisa and Faizah to finalise DB | 45 min | Charli, Faizah, Marisa | Yes
4 | 2024-11-30 | Finalised code and merged with main | 1.5 hrs | Charli | Yes
4 | 2024-11-30 | Group call | 1 hr | All except Molly | Yes
4 | 2024-11-30 | Looking into db_utils errors and trying to fix | N/A | Faizah, Phoebe, Charli | Yes
5 | 2024-12-02 | Working on adding sound effects to game | 2.5hrs+ | Charli | Yes
5 | 2024-12-02 | Group call with Ellen, Phoebe, Molly. Showed SFX and left after 5-10 mins | 10 min | Charli, Phoebe, Molly, Ellen | Yes
5 | 2024-12-04 | Working on sound effects and fixing config issue | 2 hr + | Charli | Yes
5 | 2024-12-04 | Call with Arianne to help with push/merge issue | 30 mins | Charli | Yes
5 | 2024-12-05 | Fixing SQL issue and working on merge conflicts between sound effects and main branch | 3hrs | Charli | Yes
5 | 2024-12-06 | Updated code and fixed sfx issues, merged and PR sound_effects branch to main/github | 4hrs | Charli | Yes
5 | 2024-12-06 | Look into shortening facts to help with UX in game | - | Charli | Yes
5 | 2024-12-06 | Shortened facts in mysql workbench and branched off in pycharm to create an update, PR and merged | 2hrs | Charli | Yes
5 | 2024-12-06 | Working on presentation powerpoint, wrote script for conclusion slide | 2 hrs | Charli | Yes
5 | 2024-12-09 | Wrapping up presentation before the evening rehearsal | 3 hrs | Charli, Marisa, Faizah | Ongoing
5 | 2024-12-09 | Presentation Rehearsal | 20 mins | All | Upcoming
Total time:

## Faizah
Name: | Faizah | Project Group (Name/Number): Group 4
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database, something related to science etc. Have decided to meet on 09/11 to finalise on a topic. Will discuss the next steps we can all do individually and the next date everyone is available. Have created a shared GitHub repo. | 30 minutes | All | Yes | finalise on a game idea that fits our brief
1 | 2024-11-06 | Thought about some game ideas individually, such as astronomy adventure game(space game for kids), chemistry virtual lab and other science games. | 2 hours | Faizah | Yes | share ideas with group
2 | 2024-11-09 | Had a planned group meeting to discuss our idea. Decided to choose space game via a poll as will include the features that match with the project requirements: timer, purpose to be educational and fun for kids and interactive. Discussing how to split and organise project assignment. | 1 hour | All | Yes | Go through the project assignment and complete the project tasks. Molly created canva template so will add info on there and decided as a team to go through last 2 tasks together in the next meeting(12/11).
2 | 2024-11-10 | Researching and thinking of ideas to add to shared canva doc. | 1-2 hours | Faizah | Yes
2 | 2024-11-12 | Group call to discuss our research and finalise on ideas such as timer, lives and if we should add facts or questions. discussed how we will use SQL w/ database. task allocation was set. Will be focusing on the 2nd and 3rd part of the project assignment. | 1 hour | All, Sophie was absent | Yes
2 | 2024-11-13 | Collated all the information for Q2 for the project assignment and potential ideas too | 2 hours | Faizah | Yes
2 | 2024-11-14 | Had a group meeting where Arianne had joined later on to discuss some of our questions. Was talking about ways we could split the tasks, specifically the code. | 1 hour | All, Sophie and Marisa were absent | Yes | Will be looking over pygame tutorials over the weekend, snake and platformer game to translate similar skills for our game
2 | 2024-11-16 | Going over youtube videos for pygame tutorials, basics and games | 2-3 hours | Faizah | Yes
3 | 2024-11-19 | First group meeting using Jira to create tasks. Tasks delegated based on our preference and strengths. Myself, Charli and Marisa will focus on SQL(db utilis connector and database), Pheobe, Ellen, Molly and Sophie will focus on python and creating diff classes for astronaut and asteroids etc. | 30 min-1 hour | All | Yes | Will also be starting on the project document: introduction, background as well as starting on the specifications and design. Everything to be completed by 25/11/2024.
3 | 20/11-24/11/2024 | Worked on the project document and db utilis, adjusted to ensure random facts are fetched one by one | 3-4 days | Faizah | Yes
4 | 2024-11-25 | Had a group meeting to check in with everyone to see if anyone needs any help with anything and how everyone is getting on with their tasks. | 30 minutes | All | Yes | New tasks have been delegated. Planning to have call with Marisa and Charli to combine our codes and test it together
4 | 2024-11-27 | Group meeting with Charli and Marisa to test our code together and what our next steps are. Merged my db utils file to main so charli can test with database. Ran into some problems with charli's pycharm so decided to try again individually and will update each other. | 45 minutes | Charli and Marisa | Yes | Tried it again the next morning and the merge had worked with no conflicts
4 | 2024-11-28 | Had a meeting with Arianne and group to discuss queries about testing and presentation. Was talking to the group about possible ways of testing the db utils file and talked about current ways of doing this by calling functions under dunder main. | 30 minutes | All, except Charli and Marisa | Yes
4 | 2024-11-30 | group meeting to catch up and see what is left. Tasks were split and will be working on getting random facts to come onto gameplay screen from DB with phoebe. | 30 minutes | All, except Molly | Yes
4 | 2024-11-30 | Worked on improving the db utils and testing with DB to see if facts were fetched and was working properly with some testing too. Also worked on creating facts class on python to generate random facts from DB utils to appear on gameplay screen at 10-20 intervals. Facts were successfully fetched but was not showing the whole fact. Phoebe had edited the code and Ellen is also working on the speed of the facts appearing at a slower rate. | 3-4 hours | Faizah | Yes
4 | 1/12-11/12/24 | Editing report and presentation with Charli and Marisa. | 1 week | Faizah, Charli and Marisa | Ongoing

## Marisa
Name: |  | Project Group (Name/Number):
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | Spoke with the group outside of the session to discuss our ideas, availability and next steps. | 30 minutes | All | Yes
1 | 5-9/11/2024 | Spent time researching how games are made in python, watching youtube tutorials, reading/adding to the google sheet for ideas | 2 hours | Myself | Yes
1 | 2024-11-09 | Group call - discussion of next steps, agreeing on a game and theme (space). Introduced to the Canva board for collaboration | 30 Minutes | All | Yes
1 | 2024-11-11 | Spent time adding to the Canva board | 1 hour | Myself | Yes
2 | 2024-11-12 | Group call - discussion of canva board, requirements that we wanted, delegation of questions. | 1 hour | All (exp Sophie) | Yes | I made minutes as we hadnt yet found somewhere to record for free
2 | 2024-11-12 | Worked on Questions on the canva board, formatted and uploaded | 1 hour | Myself | Yes
2 | 2024-11-16 | research on pygame, revision on SQL connector | 40 minutes | Myself | Yes
3 | 2024-11-19 | Group call - delegation of specific tasks (SQL/Python). | 1 hour | All | Yes
3 | 2024-11-20 | Worked on DB utils as assigned on Jira, searched up relevant space facts | 1 hour | Myself | Yes | DB Utils to be merged with Faizahs
4 | 2024-11-25 | Group call - general check in | 30 Minutes | All | Yes | Arranged call with Faizah/Charli
4 | 2024-11-27 | Call with Faizah & Charli (SQL) Meeting to discuss where we were at/to test our code | 45 Minutes | Myself, Faizah, Charli | Yes
4 | 2024-11-30 | Group call - final tasks delegated | 30 Minutes | All (exp Molly) | Yes | I will be working on the report
4 | 2024-11-01 | Updated project report - restructured, added in features, implementation, milestones etc | 2 hours | Myself | Yes | Emailed to Ellen who uploaded to google folder
5 | 2024-12-02 | Watched recording of meeting I was absent for | 30 mins | Myself | Yes
5 | 2024-12-02 | Assigned myself tasks of project report and presentation | 10 mins | Myself | Yes
5 | 02-06/12/2024 | Edited project report, searched out presentation themes on Canva, shared with group | 1 hour | Myself | Yes | Arranged to meet with Faizah and Phoebe on slack re report
5 | 2024-12-06 | Meeting with Faizah and Phoebe to go over the project report | 20 mins | Myself, Phoebe, Faizah | Yes
2024-06-05 | 06-08/12/2024 | Worked on presentation and project report
6 | 2024-12-08 | Worked on completion of presentation | 1 hour | Myself. Phoebe, Faizah
Total time:

## Phoebe
Name: | Phoebe | Project Group (Name/Number): 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-05 | - Discussed with the group potential ideas for the project | 40 mins | All - except Charli | Yes | Research ideas and frameworks
2 | 2024-11-09 | - Decided on a spaced themed educational interactive game | 30 mins | All | Yes
2 | 2024-11-12 | - Meeting to discuss final game design and project assignment | 1 hr | All - except Sophie | Yes | Proof read project assignment
2 | 2024-11-14 | - Catchup meeting with group, discussed with Arianne how we should approach splitting tasks | 40 mins | All - except Sophie, Marisa | Yes
2 | 2024-11-14 | - Created architecture diagram for Q4 | 1 hr | Phoebe | Yes
2 | 2024-11-15 | - Proof read project assignment, made Q1 more concise | 40 mins | Phoebe | Yes
2 | 16/11/2024 - 17/11/2024 | - Walked through a space invaders tutorial to get an idea of how pygame works and what other features could be implemented | 2 hrs | Phoebe | Yes
3 | 2024-11-19 | - Meeting to split the group into python and SQL, and delegate tasks based on that through jira | 30 mins | All | Yes
3 | 2024-11-20 | - Meeting with Arianne to discuss our project plan, user input, testing and how to include a leaderboard | 30 mins | All - except Ellen, Charli | Yes
3 | 2024-11-23 | - Meeting to start implementing code | 2 hrs | Phoebe, Molly, Ellen, Sophie | Yes
2024-04-03 | 23/11/2024 - 25/11/2024 | - Researching methods for health bar structure, watched tutorials on making a class for a health bar that decreases in increments of 3 and pushed it to github | 6 hrs | Phoebe | Yes | - Figure out how to get the health bar on to the main. screen game
4 | 2024-11-25 | - Meeting to discuss branching techniques, any additional ideas for the design and delegating tasks for next sprint | 40 mins | All - except Marisa | Yes
4 | 26/11/2024 - 28/11/2024 | - Successfully got the health bar on the main game screen | 5 hrs | Phoebe | Yes
4 | 2024-11-28 | - Meeting with Arianne to discuss content for project doc, presentation and slides | 25 mins | All - except Marisa, Charli | Yes
4 | 2024-11-30 | - Meeting to discuss tasks for next sprint | 50 mins | All - except Molly | Yes | - Merge my branch to main for the health bar, look into getting the facts on the screen with Faizah
4 | 2024-11-30 | - Technical issues, deleted branches and local repo and recloned, eventually merged the health bar to main | 2 hrs | Phoebe | Yes
4 | 2024-12-01 | - Faizah started a class for the facts and passed them on to me, I managed to make the whole fact show up on the game screen | 3 hrs | Phoebe, Faizah | Yes | - Figure out how to slow down the speed cycle of the facts to change at 20 second intervals
5 | 2024-12-02 | - Messaged Ellen to help with the speed of the facts and discussed how it should show up on screen | 1 hr 30 mins | Phoebe, Ellen | Yes
5 | 2024-12-02 | - Meeting to delegate final tasks, discussed how the facts should show on screen | 25 mins | All - except Marisa, Sophie, Faizah | Yes | - Look at manual testing and editing architecture diagram for the project document
5 | 03/12/2024 - 06/12/2024 | - Looking into manual testing and gherkin syntax, creating files for feature tests with corresponding README's and screenshots, tests done for game over, name input and high score | 3 hrs | Phoebe | Yes
5 | 2024-12-05 | Edited architecture diagram for project document | 30 mins | Phoebe | Yes
5 | 2024-12-06 | - Meeting to discuss how to write up the project document and deciding which parts are necessay | 25 mins | Phoebe, Marisa, Faizah | Yes | - Write up manual testing section, conclusion and system limitations
5 | 07/12/2024 - 08/12/2024 | - Finished manual testing for timer, write up manual testing section, system limitations and conclusion | 2 hrs | Phoebe | Yes
Total time: